## Main Project Charter
Project 3 Project Proposal Option #2 Dashboard | [5 empty] | Notes
Project Title | "Climate Insights: Unveiling Ocean-Sea Dynamics, Pandemic Pollution, and Urban Air Trends"
Project Track | Custom
The Algorithm Alchemists: Team Members | Jessica Andras
Jennifer Alvarez
Natalia Lopez
Mavin Gill
Fidel Carrillo
Project Description/Outline | This data analytics project delves into the relationship between ocean temperatures and sea level rise across the past century, shedding light on potential correlations. Additionally, it investigates the impact of COVID-19 lockdowns on regional air pollution levels, pinpointing the top 5 cities that experienced the most substantial air quality improvements. Furthermore, the project identifies and maps cities worldwide that have witnessed a concerning 10% or greater increase in air pollution over the last century, providing crucial insights into long-term urban air quality trends.
Scope | In | Geographical distribution - Global. Time: last 100 years (1923-2023)
| Out | Datasets limited to US-only data, or data that does not track at least the last 100 years.
Questions (3) | 1) What is the correlation between ocean temperatures and sea level rise over the last 100 years?
2) How did the COVID-19 Pandemic lockdown affect regional levels of air pollution? What are the top 5 cities that saw the most significant improvement in air quality?
3) Which cities saw a 10% or greater increase in air pollution over the last (100) years? Identify and map them.
Datasets to be Used | 1 | NOAA Global Mapping
| 2 | Global Warming API
| 3 | NASA Earth Data
| 4 | OpenWeather API
| 5 | Air Quality/Pollution - Data.world
Rough Breakdown of Tasks | Task |  | Owner(s) | Due | Status
| 1 | Decide dataset/project path - dashboard page with functions | All | 2023-08-17 | Completed | Path: Dashboard page with functions
| 2 | Separate project sections by person. Decide who will create the main GitHub branch. | All | 2023-08-17 | Completed
| 3 | Develop Python/Flask powered API | All | 2023-08-17 | Not Started
| 4 |  |  |  | Not Started
| 5 | Have API call finalized | All | 2023-08-21 | Not Started
| 6 |  |  |  | Not Started
| 7 | Work on HTML/CSS/Java | selected group of 3 | 2023-08-25 | Not Started
| 8 |  |  |  | Not Started
| 9 | Work on SQL Database/JS library not covered (leaning towards using chart.js - Vue was also mentioned but that is its own framework (similar to d3 I believe)) | selected group of 2 | 2023-08-25 | Not Started | https://javascript.plainenglish.io/7-javascript-libraries-for-data-manipulation-visualization-and-machine-learning-70530a898a32 | Cytoscape for visualiizations, Charts
| 10 |  |  |  | Not Started
| 11 | Work on slides/finalized visualizations | All | 2023-08-27 | Not Started
| 12 | Presentation | All | 2023-08-28 | In Progress
| 13 |  |  |  | Not Started
| 14 |  |  |  | Not Started
| 15 |  |  |  | Not Started

## Q Brainstorm
Q Brainstorm | Category | Notes/Thoughts | Time span | Geo scope - US / Global
Use the EarthData Development Portal to focus on high-level earth science data insights | Earth Science | https://www.earthdata.nasa.gov/engage/open-data-services-and-software/api |  | Global
Use GeoThermal Data to development insights towards oil/gas/renewable energy projects | GeoThermal | https://data.world/datasets/geothermal |  | Global
Generate insights towards the influence of Air Quality/Pollution on major global cities within the past year | Air Quality/Pollution | https://data.world/datasets/environment |  | Global
Focus on Global Temperature changes from the past year/2 years/5 years and develop insights/graphs that illustrate those changes | Global Temperature - API | https://global-warming.org/ |  | Global
GISS Surface Temperature Analysis | Land and Sea surface temp | https://data.giss.nasa.gov/gistemp/ | 1880-2023 | Global
Global Temperature Time Series | Global Temperature | https://datahub.io/core/global-temp |  | Global
| Sea Level Change | https://datahub.io/core/sea-level-rise | 1880-2014 | N/a
OpenWeather API | API | https://openweathermap.org/api/air-pollution |  | Global
Broad range of global datapoints with latitude and longitude. | Global Mapping | https://www.ncei.noaa.gov/access/monitoring/climate-at-a-glance/global/mapping |  | Global
US Climate Data | General US data | https://www.climate.gov/maps-data/all |  | US
Meteorological data | API | https://open-meteo.com/en/docs/climate-api
| Sea Level Change - by region | https://www.star.nesdis.noaa.gov/socd/lsa/SeaLevelRise/LSA_SLR_maps.php
Data: Global and Regional SLR Scenarios for the U.S. (CSV) (cm) | Sea Level Rise - Prediction | https://tidesandcurrents.noaa.gov/sltrends/sltrends.shtml |  | Global
Global Average Absolute Sea Level Change, 1880–2021 (cm) | Sea Level Rise - Historical | https://www.epa.gov/climate-indicators/climate-change-indicators-sea-level |  | Global
1) What is the correlation between ocean temperature and sea level rise over ___?
How did the COVID-19 Pandemic lockdown affect regional levels of air pollution? Which locations had the greatest significant change?
Identify the difference between tropical and temperate ocean temperatures
How have major historical events affected temperatures/sea level change/?
How have different major historical events affected the air quality at major cities across the globe?
Top cities with 10%+ increase in air pollution - compare and map them

## LimitationsWrite-up
USED TO CREATE SLIDES AND README FILE:
REFERENCES: used https://www.citefast.com/?s=APA7
COOL GRAPHICS:
RESOURCES: